## Sheet1
Centre Block - Urgent 12 action points in the short term at the political and diplomatic levels for the commitment of the Heads of Diplomatic Missions and authorities of the countries concerned in the Centre Block
Action Code | Action Steps description | Task to be taken by whom | Contributing Partners | Responsible for the preparation: Briefing, background paper, Mémo | Time Frame | Note
A 1 | Goal 1: A major political and diplomatic action involving CBFP Facilitation to reinvigorate Chad in its environmental commitments, particularly in PPPs and World Heritage Sites/Biosphere reserves
A.1.1. | Prepare a letter from the CBFP Facilitator addressed to the Minister of the Environment of Chad providing an update on the status of implementation of the N'Djamena Declaration | Facilitation Team - WCS | WCS-APN - Regional organizations | Facilitation Team & WCS-APN | End September 2020
A.1.2. | launch a joint action by the heads of the partners' diplomatic missions in N'Djamena to engage/awaken Chad on these environmental commitments and on the implementation of the N'Djamena declaration | Facilitation Team | WCS-APN - Donors college - Regional organizations | Facilitation Team & WCS-APN | End September 2020
A.1.3. | Organise the Facilitator visit to Ndjamena to sensitize (at the highest level) the political authorities on the implementation of the N'Djamena Declaration - This action is related to A.1.2 | Facilitation Team | WCS-APN - Donors college - Regional organizations | Facilitation Team & WCS-APN | End December 2020
A.1.4.
A.2 | Goal 2: Advocacy to obtain the enlargment (Extension) of cross-border agreements and specific protocols between Cameroon, CAR and Chad to include Sudan and Southern Sudan.
A.2.1. | Prepare a motivated letter to be transmitted by the facilitator to Sudan and Southern Sudan concerning the extension of cross-border agreements / specific protocols between Cameroon, CAR and Chad. | WCS-APN-Facilitation Team | Concerned Countries; Regional organizations; Donors college | Facilitation Team & WCS-APN | End November 2020
A.2.2. | Prepare a motivated letter from the Facilitator addressed to the Heads of Diplomatic Missions of donor countries in Sudan and Southern Sudan regarding the expansion of cross-border agreements and specific protocols | WCS-APN-CBFP Facilitation | Concerned Countries; Diplomatic Missions; Donors college | Facilitation Team & WCS-APN | End November 2020
A.2.3. | Facilitate the Organisation of a ministerial meeting between the 5 countries concerned for the enlargement of the agreements: CMR, CAR, Chad, Soudan and South Soudan. This meeting can take place alongside a Ministerial Session - CTSA of the CMR, CAR and Chad | WCS-APN-CBFP Facilitation | Concerned Countries; Regional organizations; Diplomatic Missions; CBFP Facilitation - Donors college | Facilitation Team & WCS-APN | End September 2021
A3 | Goal 3: Advocacy for the designation of Zakouma as World Heritage (currently on the tentative list) and the extension of the UNESCO Biosphere Reserve from the Bamingui-Bangoran National Park to the Vassako-Bolo - Manova-Gounda National Park and to obtain the securing of protected areas
A.3.1 | Boosting the process of designating Zakouma as a UNESCO World Heritage Site | CBFP Facilitation-UNESCO | CAR; Regional organizations; CBFP Facilitation | UNESCO - WCS- CBFP Facilitation | End of October 2020
A.3.2. | Supporting the Enlargement /Extension of the UNESCO Biosphere Reserve from Bamingui-Bangoran National Park to Vassako-Bolo National Park - WHS/ Manova-Gounda | CBFP Facilitation Team, UNESCO | CBFP Donors college - WCS-AWF | UNESCO - WCS CBFP Facilitation | End of October 2020
A.3.3. | Raise awareness -Mobilize on the urgent situation of Manovo Gounda St Floris National Park - UNESCO World Heritage as a DANGER site | CBFP Facilitation Team, UNESCO | CAR; Regional organizations | WCS; CBFP Facilitation Team; UNESCO | End of October 2020
A.3.4. | Facilitator's visit to UNESCO in Paris and to Bangui in CAR | CBFP Facilitation Team, UNESCO | CBFP Facilitation Team, UNESCO, CAR, Donors College | WCS; CBFP Facilitation Team; UNESCO | End of October 2020
A.4 | Goal 4: Advocacy for a specific bilateral transboundary agreement covering (South Chad) Zakouma - Aouk and the protected areas in the North-East of CAR (Bamingui Bangoran- Gribingui, Vassako-Bolo - Manova-Gounda)
A.4.1. | Facilitate the organization of a meeting of protected area authorities from Chad and CAR in the Framework of the centre Bloc coordination Meeting | WCS-CBFP Facilitation-FAO | CAR-Chad, Regional organizations; FAO, IOM, United Nations Peacebuilding Fund (UNPF) | WCS; CBFP Facilitation Team | End of September 2020
A.4.2. | Facilitate the organisation of a second political meeting on cross-border transhumance between Chad and the Central African Republic involving the actors concerned in order to achieve a peaceful management of cross-border transhumance - On the basis of this meeting, set up or strengthen institutional, organisational and operational communication mechanisms | FAO - CBFP Facilitation | CAR-Chad, Regional organizations; FAO, IOM, UNPF, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.3. | Prepare a Facilitator's letter to CAR and Chad for the reactivation of the bilateral agreement on livestock movements between Chad and CAR | WCS-FAO | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.4. | Advocate for the resumption of meetings of the CAR-Chad Joint Commission with particular emphasis on cross-border transhumance | CBFP Facilitation | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.5. | Advocate for the creation of a joint cross-border patrol force | WCS - CBFP Facilitation | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.6. | Prepare a letter from the Facilitator addressed to ECCAS in favour of the creation of a transhumance observatory in Central Africa to collect, disseminate information and develop scientific research on agropastoral systems in Central Africa | WCS - CBFP Facilitation | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.7. | Sensitize and mobilize to strengthen agro-pastoral infrastructures (vaccination of livestock, water, pastoral, access to basic social services for transhumant populations among others). | WCS - CBFP Facilitation - FAO | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of December 2020
A.4.8. | Prepare a letter from the Facilitator to ECCAS for the signature by the Heads of State of the Central African protocol on peaceful transhumance and articulation with the other Regional Integration Communities . | CBFP Facilitation | IOM, UNPF, Invisible Children, SOS Elephant, Donors college | FAO-WCS-APN- CBFP Facilitation Team | End of August 2020
A.5 | Goal 5. Finding Financial and Technical Partners involved in André Felix - Yata-Ngaya National Park (In CAR) and Radom National Park (South Soudan)
A.5.1. | Prepare a letter from the Facilitator informing the financial and technical partners on the urgency of resources to hire operators for the André Felix - Yata-Ngaya (CAR) national park | WCS- CBFP Facilitation | Facilitation Team, Donors college | Bloc leader and Co-leaders , CBFP Facilitation | End of December 2020
A.5.2. | Propose to UNESCO /AfDB to extend the Central African Republic Biosphere Reserve project to the André Felix National Park | UNESCO - CBFP Facilitation | UNESCO - WCS, Donors college | Bloc leader and Co-leaders, CBFP Facilitation | End of December 2020
A.5.4. | Prepare a letter from the Facilitator informing the financial and technical partners on the urgency of resources to hire operators for the Radom National Parc (Au Sud Soudan - Soudan) | WCS-CBFP Facilitatio | Facilitation Team, Donors college | Bloc leader and Co-leaders, CBFP Facilitation | End of December 2020
A.5.4.
A.6 | Goal 6. Addressing Security and Peacebuilding Challenges in the Centre Block - Major Issue
A.6.1. | Introduce in the roadmap of the Block of a component, a result on peacebuilding | WCS | AWF | WCS-APN-AWF - CBFP Facilitation | End of August 2020
A.6.2. | Prepare a letter from the CBFP Facilitator addressed to the college of donors and heads of diplomatic missions on the urgency of taking Peacebuilding into account in the framework of conservation and transhumance - for more synergy between the forces of peace, defence, security and the conservation of protected areas. | AWF-WCS | AWF-WCS | WCS-APN-AWF - CBFP Facilitatio | End of October 2020
A.6.3. | Information note from donors/diplomatic missions on the status of protected areas and transhumance | WCS-APN | Concerned Countries; Regional organizations; CBFP Facilitation | WCS- CBFP Facilitation | End of October 2020
A.6.4. | Advocacy for the inclusion of Peacebuilding Components in partners' Conservation projects and programmes | CBFP Facilitation Team | CBFP Donors college - WCS-AWF | Bloc leader and Co-leaders, CBFP Facilitation | End of October 2020
A.6.5. | Prepare a letter for appreciation and encouragement to the CAR Government for the recent deployment of security forces in the area with the support of UNMISCA, and to the main armed group (FPRC) involved in the DDRR process - Investing in peace building between transhumant and local agro-pastoralists | WCS-CBFP Facilitation | Concerned Countries; Regional organizations | Bloc leader and Co-leaders, CBFP Facilitation | End of December 2020
A.6.6. | Facilitate the Organization of a high level meeting in CAR in order to promote a coordinated inter-sectoral approach (possibly for the)/and signing of MoUs between different sectors whose contributions are necessary to ensure Conservation/ management of the protected areas and Transhumance in Bamingui-Bangoran, Vassako-Bolo, Manova-Gounda St Floris and Nana Barya in particular including the Ministry of Defence/Security, Livestock/Agriculture. | WCS-CBFP Facilitation- FAO | WCS, CAR, Regional organizations; CBFP Facilitation | Bloc leader and Co-leaders, CBFP Facilitation | End of December 2020
A.6.7. | Initiate advocacy for the inclusion of conservation issues, securing protected areas and transboundary transhumance in the peace agreements between Sudan and Southern Sudan… | WCS-CBFP Facilitation | Facilitation Team, Donors college | Bloc leader and Co-leaders, CBFP Facilitation | End of December 2020
A.6.8. | Facilitate the organization of a high-level meeting for the signing of MoUs between park managers and the peacekeeping forces (MINUSCA for CAR) and the FACA. | WCS-CBFP Facilitation
A.6.7.
A.7 | Goal 7: Advocate for the integration of traditional authorities into the transhumance management systems
A.7.1. | Take stock of existing traditional agreements on transhumance around the centre Blocks between the countries of the Centre Block. | WCS, FAO | co-leads of the block; concerned countries ; Regional organizations, CBFP Facilitation | Lead and co-leads of the block; concerned countries | End of November 2020
A.7.2. | Identify key issues for public policy and advocacy regarding the reconciliation of the transhumance's traditional systems with public administration frameworks. | WCS, FAO | co-leads of the block; concerned countries ; Regional organizations, CBFP Facilitation | co-leads of the block;; Regional organizations | End of November 2020
A.7.3. | Prepare a policy brief to be shared with the head of States concerning the integration of traditional authorities into the transhumance management systems of the centered block as an integral part of the stabilization strategy | WCS, FAO | co-leads of the block; concerned countries ; Regional organizations, CBFP Facilitation | Lead and co-leads of the block.; concerned countries , | End of November 2020
A.8 | Goal 8 A major political and diplomatic action involving CBFP Facilitation and Diplomatic Missions to engage Sudan in the N'Djamena process.
A.8.1. | Prepare a letter from the High-Level Facilitator addressed to the Sectoral Minister on the status of implementation of the N'Djamena Declaration for the blocs involving the Sudan, while thanking the Sudan for its participation in the Douala meeting of experts; | WCS | CBPF Facilitation Team ; APN, Donors college | WCS-APN | End of November 2020
A.8.2. | Initiate concerted action by the heads of diplomatic missions in Khartoum to encourage Sudan to join the process, in particular with regard to (a) the Enlargment of the cross-border agreements between CAR, Cameroon and Chad; (b) participation as an observer in the process of negotiating cross-border agreements between southern Sudan and CAR, CAR and the DRC. (c) participation at the highest level in N'Djamena 2. | CBFP Facilitation | CBPF Facilitation Team ; WCS, APN, Donors college | CBFP Facilitation-WCS | End of November 2020
A.8.2. | A visit by the Facilitator to Khartoum, Sudan - Related to Actrion A.8.2. | CBFP Facilitation | CBPF Facilitation Team ;WCS, APN, Donors college | CBFP Facilitation | End of December 2020
A.9 | Initiate the collaboration between Bloc's partners (Partners' development programmes/projects), Intelligence Services and UN peacekeeping agencies MINUSCA /forces (Barkhane (G5 Sahel)); U.S. AFRICOM
A.9.1. | The Facilitator writes a letter to the Bloc's concerned Countries + concerned Donors countries'Intelligence Services + UN peacekeeping agencies to lobby for the systematic intégration of transboundary agreements on Faunic crimes unto their opérations | CBFP Facilitation and WCS | CBPF Facilitation Team , concerned Countries , MINUSCA for CAR, FACA, U.S. AFRICOM, Barkhane , Regional Organisations | CBFP Facilitation and WCS, APN | End of November 2020
A.9.2. | Organise a High level meeting with the Bloc's partners, the Concerned countries' Intelligence Services, UN peacekeeping agencies to discuss on the best way to use the existing agreements between countries in their opérations | CBFP Facilitation and WCS | CBPF Facilitation Team ; GIZ BSB Yamoussa, concerned Countries ; (G5 Sahel)); U.S. AFRICOM) , Regional Organisations | Lead and co-leads of the block.; concerned countries , | End of November 2020
A.10 | N'Djamena 2 - Head of State Summit
A.10.1. | A letter from the CBFP Facilitator addressed to the ECCAS chairperson in gabon regarding the organisation of the Head of States' Summit | CBFP Facilitator | Concerned Countries , Regional Organisations, Donors college, Head of Missions; | ECCAS EXPERTs; facilitation team and co-leaders , CBFP | End of September 2020
A.10.2. | A letter from the CBFP Facilitator addressed to the head of mission of donors countries in Gabon | CBFP Facilitator | Concerned Countries , Regional Organisations, Donors college, Head of Missions; | ECCAS EXPERTs; facilitation team and co-leaders ; CBFP | End of September 2020
A.10.3. | Lobbying for the Signing of the ECCAS Agreement on transhumance at the next ECCAS Heads of State Summit | CBFP Facilitator | Concerned Countries , Regional Organisations, Donors college, Head of Missions; | ECCAS EXPERTs; facilitation team and co-leaders; CBFP | End of August 2020
A.10.4. | Organising N'Djamena 2 in the form of the head of States Summit | CBFP Facilitation Team | Concerned Countries , Regional Organisations, Donors college, Head of Missions; | ECCAS EXPERTs; facilitation team and co-leaders | End of December 2021
A.10.5. | Building partnership to secure donors pledges for the countries invesments programmes before the head of State Summit | CBFP Facilitation Team | CBPF donors college | Bloc Leaders; co-leaders; CBFP Facilitation | End of December 2021
A.11. | Goal 11 Source out funding for the Centre Bloc Programmatic Roadmap estimated at 35.300.000 Mio €
A.11.1. | Organise a high level meeting with donors to advocate for the funding of the West Centre roadmap (global amount of: 35.300.000 Mio €) | CBPF Facilitator | Facilitation Team, Donors college | Bloc leader and Co-leaders; CBPF Facilitation | Done
A.11.2. | Convey the letter from CBFP Facilitator to the Mission Heads of donors countries for the Bloc requesting their commitment to finance the Centre Block Roadmap (global amount of: 35.300.000 Mio €. | CBPF Facilitator | Facilitation Team, Donors college | Bloc leader and Co-leaders; CBPF Facilitation | End of October 2020
A.12 | Promote the One Health Concept Biodiversity and Zoonosis and Covid-19
A.12.1. | Call for attention via the Facilitators letter to the countries of the Centre block and their implementing partners to better manage our relationship between Human - nature and wildlife. | WCS, FAO | concerned Countries, Lead and co-leads of the block. | Lead and co-leads of the block.; concerned countries , | End of November 2020 | 7.8 billion humans exploit almost each and every ecosystem of the planet, humans and their livestock interact frequently with wildlife species and the pathogens they carry. there are 4.7 billion cattle, pigs, sheep and goats and 23.7 billion chickens on Earth! We live on an increasingly “cultivated planet,” with new species assemblages and new opportunities for pathogens to move from one species to another.
A.12.2. | Facilitate and monitor the inclusion of the One health concept in the Countries Investment Programmes for the Centre Block | WCS, FAO | concerned Countries, Lead and co-leads of the block. | Lead and co-leads of the block.; concerned countries , | End of November 2020