International conference on security, the fight against poaching, regulating transhumance and armed groups circulating between the Sahel and Equatorial Africa

Developing an operational strategy for each of the 3 priority geographical blocs

Proposed generic logical framework

(Preparing for the expert meeting /Yaoundé/ 16 - 17 December 2019)

| Results chain | Indicators |  |  |  | Hypothesis Main risks and mitigation measures |
| --- | --- | --- | --- | --- | --- |
|  | Indicators | Reference | Target | Means of verification |  |
| Impact : In and around the protected areas located within the priority bloc considered, cooperation among the security services of the States concerned, efficient anti-poaching strategies and the effective involvement of the relevant administrative agencies and stakeholders associated with the livestock sector all help reduce the impact of armed groups, keep local communities safe, protect wildlife and develop a conducive legal framework for sustainable and fair management of transhumance practices. | Number of incidents involving armed groups. Number of incidents involving armed transhumants. | Drop in number of incidents in PNG, number remains stable in Chinko in spite of external pressure from armed groups, Chinko is considered a sanctuary. Bili-Uere unstable: Invasions and incidents involving LRAs and transhumants are currently very common. Downward trend in Lantoto Stable rates in Southern Park (sadly recent incidents have left people dead (2 state officials) in the Ango territory). | Zero (0) in protected areas/To de determined by the States. Hard to set targets, pressuring armed groups not within the remit of PA managers | Internal monitoring/ LAB report |  |
|  | Density of iconic large fauna in protected areas. | PNG: increase in number of giraffes, stabilize the number of elephants Chinko: Quick re-population of PA Bili-Uere: Upward trend for chimpanzees and elephants Lantoto: Data unavailable and baseline to be established in 2020 Southern: Elephants and large elks yet to confirm trends in 2020 based on aerial inventory | Reference to IMET data Wildlife inventory and ecological monitoring reports to be added as reference | IMET |  |
|  | Public revenue from formal oversight of livestock and transhumance activities (taxes and other types of charges levies) | Experiment underway in Chinko, success with negotiations and to be achieved with Southern Park, Bili Uere (Management mechanisms need to be well established (population’s share)). The corridor must be well identified and secured. Along the entire corridor, the population must be involved (grazing areas, creation of ponds, etc.) - The Bas-Uélé Province which sought to conduct a census of transhumants in order to collect provincial taxes. Agents sent on the mission were ambushed and some died. | Potential revenue of USD 5 million per year | Financial report |  |
| Outcome 1: A clear and specific bilateral legal framework enables the security, police and judicial agencies of the States dealing with transboundary protected areas to work together to combat and crack down on unlawful practices. | I11. A legal framework on transhumance must be established in the DRC, Southern Sudan and Sudan | See CAR legal framework (Order 33 / MAE / CAB / 10 2004-Regulations on pastoralism and livestock rearing in the Central African Republic) |  |  |  |
|  | I12. A bilateral agreement between CAR-South Sudan, Sudan-South Sudan, DRC-South Sudan, CAR-DRC, Sudan-CAR, Sudan-Chad and subsequently expand a multilateral agreement (The Governor of Bas-Uélé is interested in any steps towards a meeting with his counterpart of the CAR and would like to invite him to Buta but substantial resources are needed for a joint visit) | South Sudan-DRC process underway |  |  |  |
| Outcome 11. Transboundary agreements are negotiated and signed | I111. At least 1 specific protocol to ease operations: for LAB | Protocol to be negotiated between Bili-Uéré and Chinko |  |  |  |
|  | I112. At least 1 specific protocol to ease operations: for LAB | Negotiations underway between DRC- South Sudan |  |  |  |
|  | I113. At least 1 specific protocol to ease trade operations I114. At least 1 specific protocol to ease legal cooperation | Negotiations underway between DRC- South Sudan |  |  |  |
| Activity 111 . | Activity description- Resources to be used- Costs EU: 100, 000 EUR (meetings, etc) |  |  |  |  |
| Activity 112. | Activity description- Resources to be used- Costs |  |  |  |  |
| Outcome 12 Operational bilateral technical protocols (army, interior (police), judiciary) | I121. Negotiate a specific protocol enabling cooperation between park rangers and collaboration in aerial surveillance and intelligence |  |  |  |  |
|  | I122. |  |  |  |  |
| Activity 121. | Technical negotiations |  |  |  |  |
| Activity 122. | Financing conditions are defined (items and amounts to be covered by the States’ budgets/items and amounts to be covered by the PTF) |  |  |  |  |
| Outcome 2: Anti-poaching strategies are effectively implemented by the managers of the transboundary protected areas involved, in line with the provisions of transboundary agreements (product 11) and operational technical protocols (product 12) | I21 Strategies are operational for Chinko and Garamba Awaiting extension of implementation to Bili-Uere following the signing of amendment with the EU): Awaiting finalization by the ICCN and its operationalization. Strategy to be developed and implemented for Lantoto and its surroundings Strategy to be developed and implemented for Southern National Park and its surroundings | Extend discussions of transhumance issues to neighbouring non-COMIFAC countries (work to begin on drafting of agreement between COMIFAC and IGAD to strengthen the meetings). Similarly extend to ECOWAS countries vs Cameroon, Niger, Nigeria and Chad |  |  |  |
| Outcome 21. The transboundary protected areas concerned are managed within a clear and efficient nationwide governance framework (clear, transparent and public administrative framework, territorial integrity, absence of conflicting overlaps) | I211. Management contracts are signed and in force. | Bili-Uere and Garamba management contracts are signed and in force. The Chinko management contract was signed on 15 April 2020. No management contract for Lantoto Southern Park needs to establish a specific formal framework WCS will be responsible for the Centre and East while the FFI handles the West bloc in collaboration with the minister |  |  |  |
|  | I212. The managers’ qualifications and capacities are recognized and assessed. | IMET evaluation conducted for PNG and Chinko (February 2020) Bili-Uere IMET conducted, METT is done for Lantoto by WCS and the Southern Park in 2011-2016 and an assessment will be done to update the METT |  |  |  |
| Activity 211. |  |  |  |  |  |
| Activity 212. |  |  |  |  |  |
|  | I222. Any conflicts of overlap and turf protection are resolved | No known overlap conflicts in Garamba, a few conflicts in Chinko, Land use plan underway in PNG and in Chinko Bili-Uere: no conflicts (Land use plan underway) Lantoto: no conflicts Southern Park: no conflicts? |  |  |  |
| Activity 221. |  |  |  |  |  |
| Activity 222. |  |  |  |  |  |
| Product 23 An adequate multilateral collaboration framework is developed and provides the requisite data for an efficient anti-poaching (LAB) strategy (early warning, satellite, information network…) | I221. A multilateral collaboration framework is signed and is operational | Regional Information and Coordination Centre (RICC): close collaboration between Chinko and Garamba (Management coordinated by APN under the regional responsibility of Garamba); Reports are already being sent by Chinko LAB to the RICC and analyses and reports are produced for Chinko LAB Collaboration framework to be established between Garamba and Bili-Uere: There is a real need to establish it in Garamba and Chinko: (PNG) will visit Bili to see what can be done to establish this collaboration. Negotiations on the collaboration framework between Lantoto and Garamba Southern National Park should be included in this collaborative framework with the RICC. |  |  |  |
|  | I222. |  |  |  |  |
| Activity 231. | Conduct capacity assessment and need. capacity building of government and community stakeholders, set up database and database protocols, deploy (communication) equipment, establish community conservation-security partnership etc. |  |  |  |  |
| Activity 232. | establish and support a network of community conservation-security partnerships, deploy (communication) equipment. |  |  |  |  |
| Activity 2.3.3. | Develop and implement an anti-corruption program. |  |  |  |  |
| Outcome 3: Transhumance activities are managed in a conducive regulatory framework that fosters sustainable management of the natural resources concerned and promotes the development of formal and fair economic sectors for all actors (at the local, national and sub-regional levels) | I31. | See CAR legal framework (Order 33 / MAE / CAB / 10 2004-Regulations on pastoralism and livestock rearing in the Central African Republic) |  |  |  |
|  | I32 |  |  |  |  |
| Product 31 The regulatory and administrative framework for transhumance is clarified at every level of relevant authority (local, national and sub-regional) and is promulgated and operational. | I311. A legal framework is implemented and popularized: No legal framework in the DRC. Bas - Uélé province however will welcome any initiative in this regard | Protected areas work within the framework of a national strategy |  |  |  |
|  | I312. |  |  |  |  |
| Activity 311. | Collaborations with the Ministry of Agriculture, livestock and economy -Collaborate with local authorities |  |  |  |  |
| Activity 312. | Register livestock and monitor movements |  |  |  |  |
| Activity 313. | Map out and rehabilitate recognized transhumance corridors |  |  |  |  |
| Outcome 32 Transhumance dynamics are managed within a fair and conducive economic framework | I321 Herd sizes are managed, regulated and kept under control in the countries of origin and host countries of the herds: Not being done in the DRC |  |  |  |  |
|  | I322. Accommodation capacities of recipient countries of transhumant cattle are defined in ecological, social and economic/commercial/marketing/market terms | Envisaged in Chinko but not in the DRC? |  |  |  |
|  | I323 Ecosystem services provided by host countries are compensated through taxation and parallel taxation schemes | Envisaged in Chinko but not in the DRC? Similar scheme envisioned for Bas-Uele province |  |  |  |
| Activity 321. | Enhancing the economic performance of formal and registered transhumance |  |  |  |  |
| Activity 322. | On-site expansion through innovative mechanisms |  |  |  |  |
| Product 33 A regional transhumance monitoring system is established between the States and regions concerned in consultation with protected area management and sector stakeholders, enabling active management of livestock (anticipation and concerted management of crises) | I321. The monitoring system is in place between Chinko, Garamba and Bili-Uere | The system is in place between Chinko and Garamba. To be extended to Bili-Uere |  |  |  |
|  | I322. The monitoring system enlarged to Lantoto |  |  |  | I322. The monitoring system extended to Southern Park? |
| Activity 331. |  |  |  |  |  |
| Activity 332. |  |  |  |  |  |
| Outcome 34 Studies conducted to enhance knowledge on wildlife, economic, social, political and security dynamics to promote better understanding of issues associated with transhumance. |  |  |  |  |  |
| Activity 4.11: Conduct studies on transhumance in each (transboundary) landscape: mapping out pastoralist groups, numbers, movements and associated issues, and anticipated climate change impacts. |  | WCS to conduct such a study in Southern National Park landscape in 2020. |  |  |  |
| Activity 412: Conduct regular landscape wide aerial and ground surveys to monitor wildlife, human activities and (emerging) threats. |  | Last aerial survey covering part of Southern National Park conducted in 2015-2016 by WCS. |  |  |  |
| Outcome 4: The information/communication strategy on protected areas in the priority bloc concerned is linked up with a regional concerted COM strategy that enhances the value of transboundary protected areas in Central Africa in the eyes of national /international public opinion and of the relevant global initiatives. | I41. An information / communication and public relations strategy is operational |  |  | Validation of ECOFAC 6 communication strategy during COPIL in March 2020 | Supported by PIR ECOFAC 6 |
|  | I42. A communication strategy is extended to the entire landscape concerned and to all stakeholders concerned with transhumance |  |  |  |  |
| Product 41. Contributions to a “mass” communication strategy | I411.Establish communication channels (radio, TV, etc) | Hiring envisaged for Garamba and Bili: Radio equipment available in Bili and to be installed - Also possible collaboration with Internews outlet that works with community radios to reach a wider audience |  |  |  |
|  | I412. |  |  |  |  |
| Activity 411. |  |  |  |  |  |
| Activity 412. |  |  |  |  |  |
| Outcome 42 Help develop technical lobbying documents designed to get the attention of relevant global initiatives | I421.Technical lobbying documents are developed |  |  |  |  |
|  | I422.Multi-target communication tools including conventional tools are put in place |  |  |  |  |
| Activity 421. |  |  |  |  |  |
| Activity 422. |  |  |  |  |  |